## Consulting Project Timeline
Consulting Project Timeline - Network Design & Inventory Modeling
Network Optimization - Consolidate Distribution Centers
Duration: 3-6 months
Phase | Timeline | Activity | Description
Phase 1 | Week 1-2 | Kickoff & Data Collection | Client engagement, data request, stakeholder alignment
Phase 2 | Week 3-4 | Data Validation | Data cleaning, validation, gap analysis
Phase 3 | Week 5-8 | Baseline Analysis | Current state modeling, performance metrics
Phase 4 | Week 9-12 | Scenario Development | Design alternatives, constraint definition
Phase 5 | Week 13-18 | Optimization & Analysis | Model runs, sensitivity analysis, cost-benefit
Phase 6 | Week 19-24 | Recommendations & Presentation | Final recommendations, executive presentation
Network Optimization - New Facility (Expansion)
Duration: 6-12 months
Phase | Timeline | Activity | Description
Phase 1 | Week 1-3 | Kickoff & Strategic Planning | Stakeholder alignment, business case development
Phase 2 | Week 4-6 | Data Collection & Market Analysis | Demand forecasting, market research, site analysis
Phase 3 | Week 7-10 | Baseline Network Modeling | Current network performance, capacity analysis
Phase 4 | Week 11-16 | Facility Location Analysis | Site selection, capacity planning, cost modeling
Phase 5 | Week 17-22 | Network Optimization | Multi-scenario analysis, trade-off evaluation
Phase 6 | Week 23-30 | Implementation Planning | Phased rollout, risk assessment, change management
Phase 7 | Week 31-48 | Execution & Monitoring | Facility setup, network transition, performance tracking
Network Optimization - M&A Synergies
Duration: 6-12 months
Phase | Timeline | Activity | Description
Phase 1 | Week 1-2 | Due Diligence & Assessment | Network analysis, integration planning
Phase 2 | Week 3-4 | Data Integration | Combined data sets, system alignment
Phase 3 | Week 5-10 | Baseline Analysis | Pre-merger state, synergy identification
Phase 4 | Week 11-18 | Integration Scenarios | Network consolidation options, cost analysis
Phase 5 | Week 19-26 | Optimization & Validation | Synergy quantification, risk mitigation
Phase 6 | Week 27-40 | Implementation Roadmap | Phased integration, change management
Phase 7 | Week 41-52 | Execution & Monitoring | Network consolidation, performance tracking
Network Optimization - Lane Consolidation
Duration: 1-3 months
Phase | Timeline | Activity | Description
Phase 1 | Week 1 | Kickoff & Data Collection | Lane data, shipment volumes, carrier rates
Phase 2 | Week 2 | Baseline Analysis | Current lane performance, cost analysis
Phase 3 | Week 3-4 | Consolidation Scenarios | Lane grouping, route optimization
Phase 4 | Week 5-6 | Cost-Benefit Analysis | Savings calculation, implementation planning
Phase 5 | Week 7-8 | Recommendations | Final recommendations, carrier negotiations
Phase 6 | Week 9-12 | Implementation | Lane consolidation, monitoring
Inventory Modeling - Safety Stock Optimization
Duration: Immediate - 2 months
Phase | Timeline | Activity | Description
Phase 1 | Week 1 | Kickoff & Data Collection | Historical demand, lead times, service levels
Phase 2 | Week 2 | Baseline Analysis | Current safety stock levels, stockout analysis
Phase 3 | Week 3-4 | Optimization Modeling | Service level targets, demand variability analysis
Phase 4 | Week 5-6 | Scenario Analysis | Different service levels, cost trade-offs
Phase 5 | Week 7-8 | Recommendations & Implementation | Optimal safety stock levels, system updates
Inventory Modeling - Peak Planning
Duration: 1-2 months
Phase | Timeline | Activity | Description
Phase 1 | Week 1 | Kickoff & Demand Forecasting | Historical peak data, demand patterns
Phase 2 | Week 2 | Baseline Analysis | Current peak inventory, stockout history
Phase 3 | Week 3-4 | Peak Scenario Modeling | Demand scenarios, capacity constraints
Phase 4 | Week 5-6 | Inventory Planning | Optimal stock levels, replenishment strategy
Phase 5 | Week 7-8 | Recommendations | Peak inventory plan, implementation guide
Inventory Modeling - Purchase Method Optimization
Duration: Immediate - 1 month
Phase | Timeline | Activity | Description
Phase 1 | Week 1 | Kickoff & Data Collection | Purchase history, costs, lead times
Phase 2 | Week 2 | Baseline Analysis | Current purchase methods, cost analysis
Phase 3 | Week 3 | Optimization Analysis | Cost comparison, method selection
Phase 4 | Week 4 | Recommendations | Optimal purchase methods, implementation