## Internal Company Timeline
Internal Company Timeline - Network Design & Inventory Modeling
Network Optimization - Consolidate Distribution Centers
Duration: 2-4 months
Phase | Timeline | Activity | Description
Phase 1 | Week 1 | Project Kickoff | Team alignment, data access, tool setup
Phase 2 | Week 2-3 | Data Collection & Validation | Internal data extraction, validation
Phase 3 | Week 4-6 | Baseline Analysis | Current state modeling, performance review
Phase 4 | Week 7-10 | Scenario Development | Design alternatives, what-if analysis
Phase 5 | Week 11-14 | Optimization & Analysis | Model runs, cost-benefit analysis
Phase 6 | Week 15-16 | Recommendations & Approval | Internal presentation, decision making
Network Optimization - New Facility (Expansion)
Duration: 4-8 months
Phase | Timeline | Activity | Description
Phase 1 | Week 1-2 | Project Kickoff | Strategic planning, team formation
Phase 2 | Week 3-4 | Data Collection | Demand data, cost data, market analysis
Phase 3 | Week 5-8 | Baseline & Market Analysis | Current network, market opportunities
Phase 4 | Week 9-14 | Facility Analysis | Site evaluation, capacity planning
Phase 5 | Week 15-20 | Network Optimization | Multi-scenario analysis, selection
Phase 6 | Week 21-28 | Implementation Planning | Phased approach, resource allocation
Phase 7 | Week 29-32 | Execution | Facility setup, network transition
Network Optimization - M&A Synergies
Duration: 4-8 months
Phase | Timeline | Activity | Description
Phase 1 | Week 1 | Integration Planning | Team formation, data access
Phase 2 | Week 2-3 | Data Integration | Combined datasets, system alignment
Phase 3 | Week 4-8 | Baseline & Synergy Analysis | Pre-merger state, opportunity identification
Phase 4 | Week 9-16 | Integration Scenarios | Consolidation options, cost analysis
Phase 5 | Week 17-24 | Optimization & Planning | Synergy quantification, roadmap
Phase 6 | Week 25-32 | Implementation | Network consolidation, monitoring
Network Optimization - Lane Consolidation
Duration: 1-2 months
Phase | Timeline | Activity | Description
Phase 1 | Week 1 | Data Collection | Lane data, shipment volumes, rates
Phase 2 | Week 2 | Baseline Analysis | Current performance, cost review
Phase 3 | Week 3 | Consolidation Analysis | Lane grouping, optimization
Phase 4 | Week 4 | Cost-Benefit & Decision | Savings analysis, approval
Phase 5 | Week 5-8 | Implementation | Lane consolidation, monitoring
Inventory Modeling - Safety Stock Optimization
Duration: Immediate - 1 month
Phase | Timeline | Activity | Description
Phase 1 | Week 1 | Data Collection | Historical demand, lead times, service levels
Phase 2 | Week 2 | Baseline Analysis | Current safety stock, stockout review
Phase 3 | Week 3 | Optimization | Service level analysis, optimal levels
Phase 4 | Week 4 | Implementation | System updates, monitoring
Inventory Modeling - Peak Planning
Duration: 1 month
Phase | Timeline | Activity | Description
Phase 1 | Week 1 | Demand Analysis | Historical peak data, forecasting
Phase 2 | Week 2 | Inventory Planning | Peak scenarios, stock levels
Phase 3 | Week 3 | Optimization | Optimal plan, replenishment strategy
Phase 4 | Week 4 | Implementation | Inventory plan execution
Inventory Modeling - Purchase Method Optimization
Duration: Immediate
Phase | Timeline | Activity | Description
Phase 1 | Week 1 | Data Collection | Purchase history, costs, methods
Phase 2 | Week 2 | Analysis & Optimization | Cost comparison, method selection
Phase 3 | Week 3 | Implementation | Method updates, monitoring